## Gantt
KUKA Project Gantt Chart
EG-353 2026/27. Yellow dates are editable planning inputs. All submission dates require confirmation.
Month boundaries and month-end milestones are plotting placeholders. Exam and spring-break periods are provisional.
ID | Activity | Start | Finish | Mo. | Type | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
T1 | Background research | 2026-10-01 | 2026-12-31 | 3 | Task | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
T2 | Planning and approvals | 2026-10-01 | 2026-11-30 | 2 | Task | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
T3 | Simulation validation | 2026-10-01 | 2026-11-30 | 2 | Task | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
T4 | Data preparation | 2026-11-01 | 2026-12-31 | 2 | Task | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
T5 | Numerical IK baseline | 2026-12-01 | 2026-12-31 | 1 | Task | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
T5 | Numerical IK baseline resumed | 2027-02-01 | 2027-02-28 | 1 | Task | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
T6 | Network training and integration | 2026-12-01 | 2026-12-31 | 1 | Task | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
T6 | Network and integration resumed | 2027-02-01 | 2027-03-31 | 2 | Task | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
T7 | Independent evaluation | 2027-03-01 | 2027-03-31 | 1 | Task | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
T8 | Outline and project records | 2026-10-01 | 2026-10-31 | 1 | Task | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T8 | Interim writing and records | 2026-12-01 | 2026-12-31 | 1 | Task | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
T8 | Reports and viva preparation | 2027-02-01 | 2027-05-31 | 4 | Task | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Milestones
M1 | Outline and initial plan | 2026-10-31 | Proposed | bar: 2026-10-01 to 2027-05-01
M2 | Ethics and risk review | 2026-11-30 | Proposed | bar: 2026-10-01 to 2027-05-01
M3 | Validated model and dataset | 2026-11-30 | Proposed | bar: 2026-10-01 to 2027-05-01
M4 | Numerical IK baseline | 2026-12-31 | Proposed | bar: 2026-10-01 to 2027-05-01
M5 | Progress report and network results | 2027-02-28 | Proposed | bar: 2026-10-01 to 2027-05-01
M6 | Integrated method and testing | 2027-03-31 | Proposed | bar: 2026-10-01 to 2027-05-01
M7 | Draft paper and reproducibility files | 2027-04-30 | Proposed | bar: 2026-10-01 to 2027-05-01
M8 | Final paper and viva | 2027-05-31 | Proposed | bar: 2026-10-01 to 2027-05-01
Capacity and contingency
C1 | Exam period (provisional) | 2027-01-01 | 2027-01-31 | 1 | Reduced | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
C2 | Spring break (provisional) | 2027-04-01 | 2027-04-30 | 1 | Reduced | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
B1 | Contingency and corrections | 2026-12-01 | 2026-12-31 | 1 | Buffer | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
B2 | Contingency and corrections | 2027-03-01 | 2027-03-31 | 1 | Buffer | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
B3 | Contingency and corrections | 2027-04-01 | 2027-04-30 | 1 | Buffer | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Blue = planned task. Purple = milestone. Grey = reduced capacity. Amber = reserved time. Repeated task IDs indicate separate work periods.
Source: EG-353 project outline, Gantt chart and milestones. Plan prepared 18 October 2026.

## Risk Assessment
Health Safety and Risk Assessment
Scope: computer-based modelling, data generation and machine learning in CoppeliaSim and Python.
Assessment prepared for supervisor review. Physical robot operation requires a separate assessment before any change of scope.
Faculty |  | Science and Engineering |  | Assessor | Yifeng Du 2634068
Department |  | Mechanical Engineering |  | Prepared on | 2026-10-18
Location |  | Computer workstation; confirm exact location |  | Supervisor | Dr Ashraf A. Fahmy
Documents |  | EG-353 outline and experiment records |  | Approval | Pending
Next review |  | Before experiments or a change of scope |  | Approval date
ID | What are the hazards? | Who might be harmed? | How could they be harmed? | Current controls | Further action required
R1 | Prolonged screen and keyboard use | Student | Eye strain; neck, back or wrist discomfort. | Existing workstation arrangements and break routine to be confirmed. | Review screen and desk position. Take regular breaks and vary tasks.
R2 | Electrical equipment, heat and trailing leads | Student and nearby users | Electric shock, burns or trips. | Equipment condition, ventilation and cable routing to be checked. | Use intact approved equipment. Keep vents clear, secure cables and keep liquids away.
R3 | Workload and extended experiment sessions | Student | Fatigue, stress and reduced concentration. | Plan includes contingency. Working pattern and session lengths require review. | Agree manageable work periods and regular breaks. Review workload with the supervisor.
R4 | Future physical robot work only | Operators and bystanders | Unexpected motion, impact or crushing. | Outside current simulation scope. | Before any hardware work, obtain a separate approved assessment, training and supervised operating procedure.
Current controls are unverified until checked. Supervisor approval is pending. Preparation date is not an approval date.
Source: EG-353 project outline, Health, Safety and Risk Assessment of the Project.

## Actions
Actions Arising from Risk Assessment
Update yellow status, completion-date and evidence cells after each action. Completion requires a date and supporting evidence.
ID | Action | Lead | Target or trigger | Status | Completed on | Evidence or next step
A1 | Review the risk assessment with the supervisor and obtain approval. | Student and supervisor | Before further experiments | Pending review |  | Supervisor approval required.
A2 | Complete the EG-353 safety briefing, quiz and required mini-courses. | Student | Before approval | To confirm |  | Confirm training completion and retain evidence.
A3 | Check workstation layout, equipment, ventilation and cable routing. | Student | Before extended computer work | To confirm |  | Record workstation and equipment checks.
A4 | Agree manageable working hours and regular breaks. Review workload at meetings. | Student and supervisor | At the planning review | To confirm |  | Agree working pattern at the supervisor meeting.
A5 | Complete ethics screening and submit the ethics report through the module process. | Student and supervisor | November 2026 proposed | Pending review |  | Confirm module requirements and submission date.
A6 | Review risks when scope, location or equipment changes. Complete a separate assessment before physical robot work. | Student and supervisor | Before each relevant change | Not applicable |  | Hardware is outside the current simulation scope.
A blank completion date means no completion is recorded. Review each item before marking it Complete.
Source: EG-353 project outline, Part 2 Actions arising from risk assessment.
Project Delivery Risks
Research and schedule risks are tracked separately from hazards to people.
ID | Risk | Trigger or evidence | Response | Lead | Status | Review point
P1 | Numerical IK fails to reach a valid solution. | Position error above 1 mm, invalid joints, timeout or no solution. | Check frames, joint order, limits and solver settings before network changes. | Student | Open | Numerical baseline review
P2 | The neural network provides no measurable benefit. | Same-budget comparisons show no improvement in convergence, reliability or time. | Retain the numerical baseline and report the comparison transparently. | Student | Open | Validation and final analysis
P3 | Data leakage or evaluation rules change. | Overlap with test data, tuning on test outcomes, or unrecorded rule changes. | Freeze data splits, methods and test rules. Keep every failed case in the results. | Student | Open | Before independent testing
P4 | Project files or data are lost. | Missing files, unavailable backups or version conflicts. | Back up scripts, documents and datasets. Check that important files can be recovered. | Student | Open | Regular progress reviews
P5 | Development or verification overruns the plan. | A milestone slips or unresolved defects consume reserved time. | Use the allocated contingency, revise the Gantt chart and review priorities with the supervisor. | Student and supervisor | Open | Baseline and progress report
The 1 mm threshold is a research target. This register does not state that the project has already achieved it.
Source: EG-353 project outline, Project delivery risks and KUKA 1 mm research plan.